UAE National Beverage Container Deposit Return System (DRS)

Executive Summary for Ministers

Prepared by Segen in partnership with Earth Care Consulting - for the Ministry of Economy & Tourism and the Ministry of Climate Change & Environment

July 2026 · CONFIDENTIAL - for official use only

## The opportunity

The UAE places an estimated 3.7 billion single-use beverage containers on its market each year - consumption intensity unmatched anywhere in the world - yet today's voluntary schemes recover only a low-single-digit share of that flow. With the final phase of the federal single-use plastics ban in force since 1 January 2026, beverage containers are the dominant remaining single-use stream - and the only one that can be recovered at 90%+ rates as high-grade industrial feedstock rather than prohibited. Deposit return is the proven instrument for exactly this: a 91% median return rate across European DRS countries against sub-50% for kerbside collection, with more than 400 million people already living in deposit jurisdictions.

## The proposal

Segen (Dubai) and Earth Care Consulting (European DRS specialists, with implementation roles in the Lithuanian, Slovak, Austrian and Portuguese launches and a current advisory mandate to the UK Government) propose to design, finance, build and operate the UAE's national DRS as a public-private initiative under federal sponsorship and supervision. The system is deliberately simple for consumers and rigorous for industry:

- A small, fully refundable deposit - recommended reference AED 0.25 flat per container (non-binding, for policymakers' consideration) - applied at purchase and refunded in full on return;

- A national return network of 3,500 reverse vending machines plus ~5,500 manual and HoReCa collection points - approximately 9,000 return points, one per ~1,250 residents - across supermarkets, malls, petrol stations, transit hubs and public locations;

- Three counting and sorting centres (Dubai, Abu Dhabi, Sharjah/Northern Emirates) and a central clearing platform registering every eligible container, deposit transaction and recycled tonne;

- Producer funding: recommended fees of AED 0.20 / 0.08 / 0.24 per PET / aluminium / glass container (non-binding), calibrated for steady-state cost recovery with an annual statutory fee review;

- Governance: a single, not-for-profit Deposit System Operator under two-ministry supervision, with all deposit funds held as pass-through liabilities in transparent escrow. Segen earns zero from unredeemed deposits - its income derives exclusively from operations management and the value of recovered materials.

## Headline numbers

| # | Metric | Base case |
| --- | --- | --- |
| 1 | Containers placed on market (2028 launch) | 3.74 billion/yr (PET 2.90 / cans 0.66 / glass 0.18) |
| 2 | Total CAPEX (2026-2029, phased) | AED 664 million (~AED 59 per resident) |
| 3 | Reverse vending machine fleet | 3,500 machines |
| 4 | Return-rate path | 55% (year 1) → 90% by 2034 |
| 5 | System project IRR (unlevered) | 27.7% |
| 6 | NPV @ 8% discount rate | +AED 349 million |
| 7 | Payback / peak funding need | 2031 / AED 294 million |
| 8 | Employment | ~1,200-1,500 jobs |

All figures per the study's financial model (R7 assumptions memo, 2026). The year-1 deposit float (~AED 935 million gross) is escrowed consumer money - a memo item, never revenue. PET volumes are modelled, pending producer/importer validation.

## Strategic alignment

| ▪ UAE Circular Economy Policy 2021-2031 - delivers the policy's missing operational loop: clean, food-grade recyclate returned to domestic manufacturing, with a ready-made governance home in the Circular Economy Council. | ▪ Net Zero 2050 and NDC 3.0 (−47% GHG by 2035) - a quantified, annually reported waste-sector contribution with audit-grade MRV data under the 2024 Climate Change Law. |
| --- | --- |
| ▪ The 2025 MOCCAE-Tadweer EPR pilot - the DRS nests directly into the pilot's producer-registration and reporting machinery; DRS producer fees discharge EPR obligations for beverage containers, with no double-charging. | ▪ Regional first mover - the first national, legislated DRS in the GCC; Abu Dhabi's EAD Bottle Return Scheme (23 million units collected in 2024, 100+ RVMs, 2,000+ tonnes recovered since launch) has already proven UAE consumer acceptance - without any deposit. |

The UAE at a glance - population, consumption intensity and disposal economics (data: R3/R5 market research; full source notes on chart).

## The ask

This study respectfully requests that the Ministry of Economy & Tourism and the Ministry of Climate Change & Environment:

| 1 | Adopt the DRS as the beverage-container instrument of the national Extended Producer Responsibility framework, building directly on the 2025 MOCCAE-Tadweer pilot; |
| --- | --- |
| 2 | Sponsor enabling legislation - a Cabinet Resolution under Federal Law No. 12 of 2018 establishing the deposit, the system-operator licence and the escrow regime for unredeemed deposits; international experience indicates 18-24 months from political decision to go-live, supporting a 2028 national launch; |
| 3 | Stand up a joint ministerial programme office in H2 2026 to run mobilisation (Phase 0): drafting instructions, emirate engagement and structured stakeholder consultation; |
| 4 | Convene producers, importers and retailers into a design working group under the UAE Circular Economy Council, so the final deposit level, fee schedule and return-network obligations are set with - not for - industry; |
| 5 | Commission validation of container volumes through mandatory producer/importer SKU-level reporting, converting this study's modelled estimates into a verified statutory baseline before fees are fixed. |

## Why Segen × Earth Care

| ▪ Local architect, proven implementer. Segen brings UAE alliance architecture and principal representation; Earth Care has designed and launched national deposit systems across 15+ countries - including Lithuania, the closest design template to the UAE proposal (92.3% return rate, built in under two years). | ▪ A binding financial pledge. Zero income from unredeemed deposits - stated in Segen's own Project Description and hard-wired into not-for-profit governance, statutory escrow and independent audit. |
| --- | --- |
| ▪ Financeable without public subsidy. 60/40 debt/equity on the Romanian green-loan precedent; Segen commits AED 150 million; the system pays back by 2031 and operates at cost recovery under a transparent annual fee review. | ▪ A complete, decision-ready package. Market research, 60-jurisdiction benchmark evidence, a draft legislative outline, a formula-driven financial model, an implementation roadmap and a 14-item risk register - all delivered in the accompanying Master Study. |

| The window is now. The 2026 plastics ban has cleared the field; the EPR pilot has built the regulatory machinery; consumer behaviour is proven at pilot scale. A national DRS is the logical - and financially self-sustaining - next act of the UAE's circular-economy agenda, and the only major circular-economy deliverable the UAE can bring to 90% performance within a single policy cycle. | Deposit systems outperform - return rates, DRS vs kerbside (Reloop Global Deposit Book 2024; operator reports 2025-26). |
| --- | --- |

Deposit level and producer fees are non-binding recommendations for policymaker consideration. This summary is derived from Deliverable D1 (Master Study, July 2026); all financial figures trace to the R7 financial assumptions memo and the companion financial model.